## Gantt Chart
Task ID | Milestone / Activity | Owner | Start Date | End Date | Duration (Days) | Status | Progress | Timeline (Weeks 1 - 4)
M1 | Milestone 1: Model Selection & Architecture | AI Engineer | 2026-09-01 | 2026-09-05 | 5 | Completed | 100% | ███████████████
1.1 | AI Model Selection & Evaluation (Gemini vs LaMini-Flan-T5) | AI Engineer | 2026-09-01 | 2026-09-03 | 3 | Completed | 100% | █████████
1.2 | Project Repository & Environment Architecture Setup | Full-Stack Dev | 2026-09-04 | 2026-09-05 | 2 | Completed | 100% | ██████
M2 | Milestone 2: Core Functionalities & Backend API | Backend Dev | 2026-09-06 | 2026-09-12 | 7 | Completed | 100% | █████████████████████
2.1 | Implementation of Smart Q&A Module (/qa) | AI Engineer | 2026-09-06 | 2026-09-07 | 2 | Completed | 100% | ██████
2.2 | Implementation of Concept Explainer Module (/explain) | AI Engineer | 2026-09-08 | 2026-09-09 | 2 | Completed | 100% | ██████
2.3 | Implementation of Quiz Generation Module (/quiz) | Backend Dev | 2026-09-10 | 2026-09-11 | 2 | Completed | 100% | ██████
2.4 | Implementation of Summarizer & Learning Path Modules | Backend Dev | 2026-09-11 | 2026-09-12 | 2 | Completed | 100% | ██████
2.5 | FastAPI Endpoints, Health Monitoring & Fallback Pipeline | Backend Dev | 2026-09-12 | 2026-09-13 | 2 | Completed | 100% | ██████
M3 | Milestone 3: Web Frontend Development & UI Integration | Frontend Dev | 2026-09-14 | 2026-09-19 | 6 | Completed | 100% | ██████████████████
3.1 | Dashboard Layout & 5 Feature Cards UI (HTML5/CSS3) | Frontend Dev | 2026-09-14 | 2026-09-16 | 3 | Completed | 100% | █████████
3.2 | Interactive Quiz Client with Live Grading & Score Banner | Frontend Dev | 2026-09-17 | 2026-09-18 | 2 | Completed | 100% | ██████
3.3 | Asynchronous API Integration, Spinners & Error Banners | Frontend Dev | 2026-09-18 | 2026-09-19 | 2 | Completed | 100% | ██████
M4 | Milestone 4: Testing, Verification & Deployment | QA Engineer | 2026-09-20 | 2026-09-24 | 5 | Completed | 100% | ███████████████
4.1 | Automated Pytest Suite Implementation (37 test cases) | QA Engineer | 2026-09-20 | 2026-09-21 | 2 | Completed | 100% | ██████
4.2 | Playwright Automation, Real Screenshots & Video Capture | QA Engineer | 2026-09-22 | 2026-09-23 | 2 | Completed | 100% | ██████
4.3 | Final Phase Documentation, Packaging & Zip Release | Tech Writer | 2026-09-23 | 2026-09-24 | 2 | Completed | 100% | ██████